## UAT Checklist
TC-ID | Category | Test Case | Test Steps | Expected Result | Actual Result | Status | Priority | Assigned To | Environment | Date Tested | Defect ID | Notes
TC-001 | Authentication & Access | Login with valid credentials | 1. Navigate to login page 2. Enter valid username/password 3. Click Login | User is authenticated and redirected to dashboard |  |  | Critical
TC-002 | Authentication & Access | Login with invalid credentials | 1. Navigate to login page 2. Enter invalid credentials 3. Click Login | Error message displayed; no access granted |  |  | Critical
TC-003 | Authentication & Access | Session timeout handling | 1. Login successfully 2. Remain idle beyond timeout threshold 3. Attempt an action | Session expires; user redirected to login with appropriate message |  |  | High
TC-004 | Authentication & Access | Role-based access control | 1. Login as each role (admin, user, viewer) 2. Attempt restricted actions per role | Actions blocked/allowed per role permissions matrix |  |  | Critical
TC-005 | Authentication & Access | Password reset flow | 1. Click Forgot Password 2. Enter registered email 3. Follow reset link 4. Set new password | Password updated successfully; old password no longer works |  |  | High
TC-006 | Authentication & Access | MFA enforcement | 1. Enable MFA on account 2. Logout and login again 3. Complete MFA challenge | Access granted only after MFA verification |  |  | High
TC-007 | Core Functionality | Create new record | 1. Navigate to creation form 2. Fill all required fields with valid data 3. Submit | Record created successfully; confirmation displayed; record visible in list |  |  | Critical
TC-008 | Core Functionality | Edit existing record | 1. Select an existing record 2. Modify one or more fields 3. Save changes | Changes persisted; updated values reflected in UI and database |  |  | Critical
TC-009 | Core Functionality | Delete record | 1. Select a record 2. Click Delete 3. Confirm deletion | Record removed; no longer appears in list; dependent data handled |  |  | High
TC-010 | Core Functionality | Search / filter records | 1. Enter search term or apply filters 2. Review results | Only matching records displayed; results accurate and performant |  |  | High
TC-011 | Core Functionality | Bulk operations | 1. Select multiple records 2. Apply bulk action (export, delete, update) 3. Confirm | Action applied to all selected records; partial failures reported |  |  | Medium
TC-012 | Core Functionality | Sorting and pagination | 1. Click column headers to sort 2. Navigate between pages | Sorting is accurate; pagination preserves sort order and filters |  |  | Medium
TC-013 | Input Validation | Required field enforcement | 1. Leave required fields blank 2. Submit form | Submission blocked; inline validation errors on each required field |  |  | Critical
TC-014 | Input Validation | Max length / boundary values | 1. Enter values at min, max, and beyond boundary 2. Submit | Values within bounds accepted; out-of-bounds rejected with clear message |  |  | High
TC-015 | Input Validation | Special characters / injection | 1. Enter SQL injection strings, XSS payloads, special chars in inputs 2. Submit | Input sanitized; no injection executed; appropriate error shown |  |  | Critical
TC-016 | Input Validation | Date / numeric format validation | 1. Enter invalid date formats or non-numeric values in numeric fields 2. Submit | Invalid formats rejected; guidance on expected format provided |  |  | High
TC-017 | Input Validation | File upload validation | 1. Upload files of unsupported type/size 2. Upload valid file | Invalid files rejected with clear message; valid files processed correctly |  |  | High
TC-018 | Data Integrity | Data persistence after save | 1. Create/edit a record 2. Log out and back in 3. Navigate to the record | Data matches what was saved; no loss or corruption |  |  | Critical
TC-019 | Data Integrity | Concurrent edit handling | 1. Open same record in two sessions 2. Edit and save in both | Conflict detected; appropriate resolution (last-write-wins, merge, or lock) |  |  | High
TC-020 | Data Integrity | Referential integrity | 1. Delete a parent record with child dependencies 2. Verify child records | Cascade/restrict behavior matches business rules; no orphan records |  |  | High
TC-021 | Data Integrity | Audit trail / change log | 1. Perform create, update, delete 2. Check audit log | All actions logged with timestamp, user, before/after values |  |  | High
TC-022 | Data Integrity | Backup and restore | 1. Take backup 2. Modify/delete data 3. Restore from backup | Data restored accurately to backup point; no corruption |  |  | Medium
TC-023 | Integration & API | Third-party API connectivity | 1. Trigger integration call 2. Verify response data | External API called; response data correctly mapped and displayed |  |  | High
TC-024 | Integration & API | API error handling | 1. Simulate API timeout/failure 2. Observe application behavior | Graceful degradation; error message shown; no data loss; retry where applicable |  |  | High
TC-025 | Integration & API | Webhook / callback processing | 1. Trigger event that fires webhook 2. Verify target system received payload | Payload delivered with correct schema; idempotent on retry |  |  | Medium
TC-026 | Integration & API | Data sync between systems | 1. Update data in source system 2. Wait for sync interval 3. Verify in target system | Data consistent between systems within SLA; conflicts logged |  |  | High
TC-027 | Notifications & Alerts | Email notifications triggered | 1. Perform action that triggers email 2. Check inbox | Email received within SLA; content accurate; links functional |  |  | High
TC-028 | Notifications & Alerts | In-app notifications | 1. Trigger notification event 2. Check notification panel | Notification appears in real-time; mark-as-read works; links navigate correctly |  |  | Medium
TC-029 | Notifications & Alerts | Alert threshold triggers | 1. Create condition exceeding alert threshold 2. Monitor alerts | Alert fired at correct threshold; correct recipients notified |  |  | Medium
TC-030 | Reporting & Export | Report generation | 1. Select report type and parameters 2. Generate report | Report generated with accurate data matching filters; totals correct |  |  | High
TC-031 | Reporting & Export | Export to CSV/Excel/PDF | 1. Apply filters to data view 2. Click Export 3. Open exported file | File downloads; data matches filtered view; formatting intact |  |  | High
TC-032 | Reporting & Export | Dashboard accuracy | 1. Compare dashboard widgets to underlying data 2. Apply date range filters | All metrics, charts, and KPIs match source data; filters update all widgets |  |  | High
TC-033 | Performance | Page load time | 1. Navigate to each major page 2. Measure load time | Pages load within acceptable threshold (e.g., <3s on standard connection) |  |  | High
TC-034 | Performance | Large dataset handling | 1. Load view with 10K+ records 2. Apply sort/filter/search | No timeout or crash; results returned within SLA; pagination works |  |  | Medium
TC-035 | Performance | Concurrent user load | 1. Simulate N concurrent users 2. Monitor response times and errors | Response time degrades gracefully; no errors under expected load |  |  | Medium
TC-036 | UI / UX | Cross-browser compatibility | 1. Execute core workflows in Chrome, Firefox, Safari, Edge | Consistent behavior and layout across all supported browsers |  |  | High
TC-037 | UI / UX | Mobile / responsive layout | 1. Access app on mobile device or resize browser 2. Test core flows | Layout adapts; all functions accessible; no overlapping elements |  |  | Medium
TC-038 | UI / UX | Accessibility - Web Content Accessibility Guidelines (WCAG) | 1. Test with screen reader 2. Check keyboard navigation 3. Verify contrast ratios | All interactive elements accessible; ARIA labels present; contrast compliant |  |  | Medium
TC-039 | UI / UX | Error state display | 1. Trigger various error conditions 2. Observe error messages | User-friendly messages; no stack traces or technical jargon exposed |  |  | High
TC-040 | UI / UX | Loading states and feedback | 1. Trigger long-running operations 2. Observe UI behavior | Loading indicator shown; UI not frozen; cancel option where applicable |  |  | Medium
TC-041 | Security | Data encryption at rest and in transit | 1. Inspect network traffic (HTTPS) 2. Verify DB encryption config | All traffic over TLS; sensitive data encrypted at rest |  |  | Critical
TC-042 | Security | CSRF / XSS protection | 1. Attempt cross-site request forgery 2. Attempt stored/reflected XSS | CSRF tokens enforced; XSS payloads sanitized and not executed |  |  | Critical
TC-043 | Security | Sensitive data masking | 1. View screens displaying PII/secrets 2. Check API responses | SSNs, passwords, tokens, etc. masked in UI and API responses |  |  | Critical
TC-044 | Security | API authentication enforcement | 1. Call API endpoints without auth token 2. Call with expired token | Unauthenticated requests return 401; expired tokens return 401/403 |  |  | Critical
TC-045 | Security | Rate limiting | 1. Send rapid successive requests to API 2. Observe responses | Rate limit enforced; 429 returned after threshold; no service degradation |  |  | High
TC-046 | Error Handling & Recovery | Graceful failure on dependency outage | 1. Disable a downstream service 2. Perform dependent operation | User-friendly error; no data loss; system recovers when service restored |  |  | High
TC-047 | Error Handling & Recovery | Transaction rollback on failure | 1. Initiate multi-step operation 2. Simulate failure mid-way | Partial changes rolled back; data consistent; user notified |  |  | High
TC-048 | Error Handling & Recovery | Retry and idempotency | 1. Submit same request multiple times (double-click, refresh) 2. Check data | No duplicate records created; operation idempotent |  |  | High
TC-049 | Deployment & Environment | Config parity across environments | 1. Compare config between UAT and Prod 2. Flag differences | All intentional differences documented; no accidental config drift |  |  | High
TC-050 | Deployment & Environment | Database migration verification | 1. Run migration scripts 2. Verify schema changes 3. Check existing data | Schema updated correctly; existing data intact; rollback tested |  |  | Critical
TC-051 | Deployment & Environment | Smoke test post-deployment | 1. Execute critical path flows after deployment 2. Check logs for errors | Core flows pass; no new errors in logs; system health checks green |  |  | Critical

## Summary
UAT Execution Summary
Total Test Cases | 51 | Category | Total | Pass | Fail
Pass | 0 | Authentication & Access | 6 | 0 | 0
Fail | 0 | Core Functionality | 6 | 0 | 0
Blocked | 0 | Input Validation | 5 | 0 | 0
Not Tested | 0 | Data Integrity | 5 | 0 | 0
In Progress | 0 | Integration & API | 4 | 0 | 0
Deferred | 0 | Notifications & Alerts | 3 | 0 | 0
|  | Reporting & Export | 3 | 0 | 0
Pass Rate (%) | 0 | Performance | 3 | 0 | 0
Completion Rate (%) | 0 | UI / UX | 5 | 0 | 0
|  | Security | 5 | 0 | 0
|  | Error Handling & Recovery | 3 | 0 | 0
|  | Deployment & Environment | 3 | 0 | 0

## Instructions
UAT Checklist — Instructions
1. UAT Checklist tab: Contains all test cases organized by category.
2. For each test case, execute the steps and record Actual Result.
3. Set Status using the dropdown: Pass / Fail / Blocked / Not Tested / In Progress / Deferred.
4. If a defect is found, log it in your defect tracker and record the Defect ID.
5. Summary tab: Auto-calculates pass rate, completion rate, and per-category breakdown.
6. Add new test cases by inserting rows within the checklist (keep within filter range).
7. Customize categories, priorities, and environments to match your project.
Status Definitions:
Pass — Test executed; actual result matches expected result.
Fail — Test executed; actual result does NOT match expected result.
Blocked — Cannot execute due to environment, dependency, or defect.
Not Tested — Not yet attempted.
In Progress — Execution started but not complete.
Deferred — Intentionally postponed to a later cycle.