## Question Generation
Module | Detailed Task | Estimated Hours | Estimated Days (8h/day)
Task 1 - Question Generation + Admin UI | Functional design & schema modeling | 4 | 0.5
Task 1 - Question Generation + Admin UI | Question DB schema + migration | 5 | 0.625
Task 1 - Question Generation + Admin UI | Question generation logic | 8 | 1
Task 1 - Question Generation + Admin UI | Prompt tuning | 5 | 0.625
Task 1 - Question Generation + Admin UI | CRUD APIs | 12 | 1.5
Task 1 - Question Generation + Admin UI | Admin UI – List + Form screens | 14 | 1.75
Task 1 - Question Generation + Admin UI | Validation + integration wiring | 6 | 0.75
Task 1 - Question Generation + Admin UI | Unit + integration testing | 6 | 0.75
Task 2 - Show Questions + Answer Capture | Fetch questions API | 4 | 0.5
Task 2 - Show Questions + Answer Capture | Integrate into submission flow | 8 | 1
Task 2 - Show Questions + Answer Capture | Dynamic rendering | 8 | 1
Task 2 - Show Questions + Answer Capture | Answer schema design | 4 | 0.5
Task 2 - Show Questions + Answer Capture | Save/Update answer APIs | 8 | 1
Task 2 - Show Questions + Answer Capture | Validation logic | 5 | 0.625
Task 2 - Show Questions + Answer Capture | Testing | 6 | 0.75
Task 3 - Admin Portal Integration | RBAC wiring | 5 | 0.625
Task 3 - Admin Portal Integration | Menu + routing integration | 3 | 0.375
Task 3 - Admin Portal Integration | Basic audit logging | 5 | 0.625
Task 3 - Admin Portal Integration | Testing | 4 | 0.5
Task 4 - CRUD + Automated Version Control | Version schema design | 6 | 0.75
Task 4 - CRUD + Automated Version Control | Auto version increment logic | 6 | 0.75
Task 4 - CRUD + Automated Version Control | Snapshot persistence | 8 | 1
Task 4 - CRUD + Automated Version Control | Rollback logic | 8 | 1
Task 4 - CRUD + Automated Version Control | Version history API | 6 | 0.75
Task 4 - CRUD + Automated Version Control | Version history UI | 8 | 1
Task 4 - CRUD + Automated Version Control | Testing | 8 | 1
TOTAL |  | 170 | 21.25